## RSA - CVR
ROAD SAFETY AUTHORITY - PUBLIC SPENDING CODE 2013 PROCUREMENT LIST
Details of Procurements in Excess of €2m, whether new, in progress or completed
Project Details:
Year | 2013
Parent Department | Department of Transport Tourism & Sport
Name of Contracting Body | Road Safety Authority
Name of Project/Description | COMMERCIAL VEHICLE REFORM PROGRAMME
Procurement Details:
Advertisement Date: | 2012
Tender Advertised in: | 2012
Awarded to: | SGS Limited
EU contract award notice date | 2012
Contract Price | € 24M
Progress:
Start Date: | 2012-05-22
Expected Date of Completion per Contract | 2018-01-21
Spend in Year under Review (2013): | € 5.3M
Cumulative Spend to end Year | € 5.3M
Projected final cost | € 24M
Value of Contract variations: | N/A
Date of Completion: | 2018-01-21
Outputs:
Expected output on completion (e.g. X km of road, no. of units) | COVIS System and Managed Delivery of Service
Output achieved to date (e.g. Y km of road, no. of units)

## RSA AGNE
ROAD SAFETY AUTHORITY - PUBLIC SPENDING CODE 2013 PROCUREMENT LIST
Details of Procurements in Excess of €2m, whether new, in progress or completed
Project Details:
Year | 2013
Parent Department | Department of Transport Tourism & Sport
Name of Contracting Body | Road Safety Authority
Name of Project/Description | NATIONAL DRIVER LICENCE SERVICE - AGENT NETWORK CONTRACT
Procurement Details:
Advertisement Date: | 2012
Tender Advertised in: | 2012
Awarded to: | SGS Limited
EU contract award notice date | 2012
Contract Price | € 18M
Progress:
Start Date: | 2013-10-29
Expected Date of Completion per Contract | 2017-10-28
Spend in Year under Review (2013): | € 1.2M
Cumulative Spend to end Year | € 1.2M
Projected final cost | € 18M
Value of Contract variations: | N/A
Date of Completion: | 2017-10-28
Outputs:
Expected output on completion (e.g. X km of road, no. of units) | Operation of an Agent Network of 34 Branches of NDLS
Output achieved to date (e.g. Y km of road, no. of units)

## RSA CLPU
ROAD SAFETY AUTHORITY - PUBLIC SPENDING CODE 2013 PROCUREMENT LIST
Details of Procurements in Excess of €2m, whether new, in progress or completed
Project Details:
Year | 2013
Parent Department | Department of Transport Tourism & Sport
Name of Contracting Body | Road Safety Authority
Name of Project/Description | NATIONAL DRIVER LICENCE SERVICE - CENTRAL LICENCING PROCESSING UNIT CONTRACT
Procurement Details:
Advertisement Date: | 2012
Tender Advertised in: | 2012
Awarded to: | ABTRAN LIMITED
EU contract award notice date | 2012
Contract Price | € 36M
Progress:
Start Date: | 2013-10-29
Expected Date of Completion per Contract | 2018-10-28
Spend in Year under Review (2013): | € 3.4M
Cumulative Spend to end Year | € 3.4M
Projected final cost | € 36M
Value of Contract variations: | N/A
Date of Completion: | 2018-10-28
Outputs:
Expected output on completion (e.g. X km of road, no. of units) | Operation of the Licence Processing Unit for the NDLS
Output achieved to date (e.g. Y km of road, no. of units)

## RSA PCDU
ROAD SAFETY AUTHORITY - PUBLIC SPENDING CODE 2013 PROCUREMENT LIST
Details of Procurements in Excess of €2m, whether new, in progress or completed
Project Details:
Year | 2013
Parent Department | Department of Transport Tourism & Sport
Name of Contracting Body | Road Safety Authority
Name of Project/Description | NATIONAL DRIVER LICENCE SERVICE - LICENCE CARD PRODUCTION CONTRACT
Procurement Details:
Advertisement Date: | 2012
Tender Advertised in: | 2012
Awarded to: | CREDIT CARD SYSTEM LIMITED
EU contract award notice date | 2012
Contract Price | € 14.5M
Progress:
Start Date: | 2013-01-01
Expected Date of Completion per Contract | 2017-12-31
Spend in Year under Review (2013): | € 2.6M
Cumulative Spend to end Year | € 2.6M
Projected final cost | € 14.5M
Value of Contract variations: | N/A
Date of Completion: | 2017-12-31
Outputs:
Expected output on completion (e.g. X km of road, no. of units) | Production of Actual Driving Licence Cards for the NDLS
Output achieved to date (e.g. Y km of road, no. of units)

## RSA BV
ROAD SAFETY AUTHORITY - PUBLIC SPENDING CODE 2013 PROCUREMENT LIST
Details of Procurements in Excess of €2m, whether new, in progress or completed
Project Details:
Year | 2013
Parent Department | Department of Transport Tourism & Sport
Name of Contracting Body | Road Safety Authority
Name of Project/Description | COMMERCIAL VEHICLE REFORM PROGRAMME - TECHNICAL INSPECTION CONTRACT
Procurement Details:
Advertisement Date: | 2012
Tender Advertised in: | 2012
Awarded to: | BUREAU VERITAS
EU contract award notice date | 2012
Contract Price | € 7.2m
Progress:
Start Date: | 2012-12-21
Expected Date of Completion per Contract | 2017-12-31
Spend in Year under Review (2013): | € 0.58m
Cumulative Spend to end Year | € 0.58m
Projected final cost | € 7.2m
Value of Contract variations: | N/A
Date of Completion: | 2017-12-31
Outputs:
Expected output on completion (e.g. X km of road, no. of units) | Delivery of Technical Inspections under Commercial Vehicle Reform System
Output achieved to date (e.g. Y km of road, no. of units)